## Backlog
Product Name | Dominion Pursuit
Team Members | Anil
Bhuwan
Christopher
Total Features | Task Left | Completed | Sprint Ends
Start | 50
Sprint 1 | 45 | 5 | 2019-02-14
Sprint 2 | 40 | 5 | 2019-02-21
Sprint 3 | 36 | 4 | 2019-02-28
Sprint 4 | 33 | 3 | 2019-03-07
Sprint 5 | 31 | 2 | 2019-03-21
Sprint 6 | 27 | 4 | 2019-03-28
Sprint 7 | 24 | 3 | 2019-04-04
Sprint 8 | 17 | 7 | 2019-04-11
Sprint 9 | 17
Sprint 10 | 17
Task ID | Priority | Status | Expected Sprint | Actual Sprint | Task Overview | Type
SET | 1 | COM | 1 | 1 | Software setup | Setup
TUT | 2 | COM | 1 | 1 | Watch tutorials | Tutorial
ASN | 3 | COM | 1 | 1 | Inception review | Assignment
PRA | 4 | COM | 1 | 1 | Practice using inkscape | Practice
PLN | 5 | COM | 1 | 1 | Plan the components of the game | Planning
REV | 6 | COM | 2 | 2 | Review the tasks for sprint 2 | Review
ASN1 | 7 | COM | 2 | 2 | Iteration 1 | Assignment
TUT2 | 8 | COM | 2 | 2 | Tutorial on Github Basics | Tutorial
GRA | 9 | COM | 2 | 2 | Design game graphics | Graphics
COD | 10 | COM | 2 | 2 | Develop game scripts | Coding
ASN1.2 | 11 | COM | 2 | 3 | Iteration 1 review | Assignment
GRA | 12 | COM | 3 | 3 | Design character graphics | Graphics
COD | 13 | COM | 3 | 6 | Implement multi-character mode | Coding
PLN | 14 | COM | 3 | 3 | Plan out the main menu screen | Planning
GRA | 15 | COM | 3 | 3 | Design number graphics | Graphics
IMP | 16 | COM | 3 | 4 | Incorporate the number graphics | Implementation
GRA | 17 | COM | 4 | 4 | Design more character graphics | Graphics
DOC | 18 | COM | 4 | 4 | Document the character details | Documentation
ASN2 | 19 | COM | 5 | 5 | Iteration 2 | Assignment
ASN2.2 | 20 | COM | 5 | 5 | Iteration 2 review | Assignment
COD | 21 | COM | 6 | 6 | Implement basic character interactions | Coding
REV | 22 | COM | 6 | 7 | Code review | Review
DEG | 23 | COM | 6 | 6 | Design game screen options | Design
DEG | 24 | COM | 6 | 6 | Design event cards | Design
OPT | 25 | COM | 7 | 7 | Code optimization | Optimization
IMP | 26 | COM | 7 | 8 | Implement menu system | Implementation
COD | 27 | NS | 7 |  | Game end scenario | Coding
DEG | 28 | COM | 7 | 7 | Design tile effects | Design
COD | 29 | IP | 8 | 8 | Implement AI system | Coding
ASN | 30 | COM | 8 | 8 | Iteration 3 | Assignment
MIS | 31 | NS | 8 | 8 | Search for sound effects | Miscellaneous
IMP | 32 | IP | 8 | 8 | Implement tile effects | Implementation
GRA | 33 | IP | 8 | 8 | Design tile effect graphics | Graphics
COD | 34 | COM | 8 | 8 | Setup message box system | Coding
ASN | 35 | NS | 9 |  | Iteration 3 review | Assignment
COD | 36 | NS | 9 |  | Implement sound system | Assignment
OPT | 37 | NS | 9 |  | Code and AI optimization | Optimization
COD | 38 | NS | 9 |  | Implement event cards | Implementation
IMP | 39 | NS | 9 |  | Implement message displays | Implementation
IMP | 40 | NS | 9 |  | Add functionality to main menu buttons | Implementation
TES | 41 | NS | 9 |  | Manual test and report bug | Testing
42
43
44
45
46
47
48
49
50

## Sprint1
Sprint # | 1
Start on | 2019-02-08
End on | 2019-02-14
Total Tasks | 12 | Feb
Day 1 Left | 12 | 8
Day 2 Left | 10 | 9 |  |  |  |  | NOTE
Day 3 Left | 6 | 10
Day 4 Left | 6 | 11 |  |  |  |  | Please only update the Status (NOT the color) of the task that you are assigned to.
Day 5 Left | 6 | 12
Day 6 Left | 5 | 13
Day 7 Left | 0 | 14
Status
[7 empty] | NS | Not Started
S.N. | Task ID | Type | Assigned To | Description | Status | Notes | IP | In Progress
1 | SET | Setup | Bhuwan | Design a scrum for the project | COM |  | COM | Completed
2 | SET | Setup | Anil | Download and install Unity & Inkscape | COM | Unity 2018.3.0 |  | Needs Attention
3 | SET | Setup | Christopher | Download and install Unity & Inkscape | COM | Unity 2018.3.0
4 | TUT | Tutorial | Anil | Watch tutorials on Inkscape and get familiar with it | COM
5 | TUT | Tutorial | Christopher | Watch tutorials on Inkscape and get familiar with it | COM | Familiar but no tutorial | Last Updated By
6 | ASG | Assignment | Bhuwan | Review the inception report of team 8 | COM
7 | ASG | Assignment | Anil | Review the inception report of team 8 | COM |  | Bhuwan
8 | ASG | Assignment | Christopher | Review the inception report of team 8 | COM
9 | ASG | Assignment | Bhuwan | Submit the review | COM | Due 02/10
10 | PRA | Practice | Anil | Draw 2 basic images on Inkscape | COM
11 | PRA | Practice | Christopher | Draw 2 basic images on Inkscape | COM
12 | PLN | Planning | Bhuwan | Plan out the components of the game to present it in next meeting to discuss upon | COM

## Sprint2
Sprint # | 2
Start on | 2019-02-15
End on | 2019-02-21
Total Tasks | 15 | Feb |  |  |  |  | NOTE
Day 1 Left | 13 | 15
Day 2 Left | 11 | 16 |  |  |  |  | Please only update the Status (NOT the color) of the task that you are assigned to.
Day 3 Left | 5 | 17
Day 4 Left | 5 | 18
Day 5 Left | 5 | 19
Day 6 Left | 5 | 20
Day 7 Left | 3 | 21 |  |  |  |  | Status
[7 empty] | NS | Not Started
[7 empty] | IP | In Progress
[7 empty] | COM | Completed
S.N. | Task ID | Type | Assigned To | Description | Status | Comments |  | Needs Attention
1 | REV | Review | Anil | Review the assigned tasks for sprint 2 | COM |  | MOV | Moved to next sprint
2 | REV | Review | Christopher | Review the assigned tasks for sprint 2 | COM
3 | ASN1 | Assignment | Anil | Assist Bhuwan & Christopher to complete the assignment | COM |  | Last Updated By
4 | ASN1 | Assignment | Bhuwan | Have a working software ready for iteration 1 | COM
5 | ASN1 | Assignment | Christopher | Create a PowerPoint for iteration 1 | COM |  | Bhuwan
6 | ASN1 | Assignment | Everyone | Hold a meeting to plan for iteration 1 | COM
7 | ASN1 | Assignment | Anil | Review docs and submit them | COM | Due 02/18 - 9 am
8 | TUT2 | Assignment | Everyone | Tutorial on GitHub by Bhuwan | COM
9 | GRA | Graphics | Bhuwan | Create some graphics needed for the game | COM
10 | GRA | Graphics | Anil | Create assigned graphics for the game | COM
11 | GRA | Graphics | Christopher | Create assigned graphics for the game | COM
12 | COD | Coding | Bhuwan | Code some scripts needed for the game | COM | Current needs only
13 | ASN1.2 | Assignment | Bhuwan | Review the iteration document of team 8 and fill up the table | MOV
14 | ASN1.2 | Assignment | Anil | Review the iteration document of team 8 and fill up the table | MOV
15 | ASN1.2 | Assignment | Christopher | Review the iteration document of team 8 and fill up the table | MOV

## Sprint3
Sprint # | 3
Start on | 2019-02-22
End on | 2019-02-28
Total Tasks | 14 | Feb
Day 1 Left | 14 | 22
Day 2 Left | 10 | 23
Day 3 Left | 7 | 24
Day 4 Left | 7 | 25
Day 5 Left | 7 | 26
Day 6 Left | 7 | 27
Day 7 Left | 2 | 28
S.N. | Task ID | Type | Assigned To | Description | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for sprint 3 | COM
2 | REV | Review | Christopher | Review the assigned tasks for sprint 3 | COM |  | NS | Not Started
3 | ASN1.2 | Assignment | Bhuwan | Review the iteration document of team 8 and fill up the table | COM |  | IP | In Progress
4 | ASN1.2 | Assignment | Anil | Review the iteration document of team 8 and fill up the table | COM |  | COM | Completed
5 | ASN1.2 | Assignment | Christopher | Review the iteration document of team 8 and fill up the table | COM |  |  | Needs Attention
6 | ASN1.2 | Assignment | Anil | Submit the review document | COM | Due - Monday 02/25 | MOV | Moved to next sprint
7 | GRA | Graphics | Anil | Design character graphics | COM | More info on Google Drive - Graphics file
8 | GRA | Graphics | Christopher | Design character graphics | COM | More info on Google Drive - Graphics file | Last Updated By
9 | GRA | Graphics | Bhuwan | Design character graphics | COM | More info on Google Drive - Graphics file
10 | COD | Coding | Bhuwan | Implement turn-based dice roll system | COM |  | Bhuwan
11 | COD | Coding | Bhuwan | Implement multi-character mode | MOV | To sprint 5
12 | PLN | Planning | Christopher | Plan out the main menu screen | COM
13 | GRA | Graphics | Anil | Design number graphics | COM | Get instructions from Bhuwan
14 | IMP | Implementation | Anil | Incorporate the number graphics | MOV | To sprint 4

## Sprint4
Sprint # | 4
Start on | 2019-03-01
End on | 2019-03-07
Total Tasks | 9 | March
Day 1 Left | 9 | 1
Day 2 Left | 9 | 2
Day 3 Left | 9 | 3
Day 4 Left | 9 | 4
Day 5 Left | 9 | 5
Day 6 Left | 7 | 6
Day 7 Left | 0 | 7
S.N. | Task ID | Type | Assigned To | Description | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for sprint 3 | COM
2 | REV | Review | Christopher | Review the assigned tasks for sprint 3 | COM |  | NS | Not Started
3 | IMP | Implementation | Anil | Incorporate the number graphics | COM |  | IP | In Progress
4 | GRA | Graphics | Anil | Design more character graphics | COM | More info on Google Drive - Graphics file | COM | Completed
5 | GRA | Graphics | Christopher | Design more character graphics | COM | More info on Google Drive - Graphics file |  | Needs Attention
6 | GRA | Graphics | Bhuwan | Design more character graphics | COM | More info on Google Drive - Graphics file | MOV | Moved to next sprint
7 | DOC | Documentation | Anil | Fill up the table with character details | COM | Character file on Google Drive
8 | DOC | Documentation | Bhuwan | Fill up the table with character details | COM | Character file on Google Drive | Last Updated By
9 | DOC | Documentation | Christopher | Fill up the table with character details | COM | Character file on Google Drive
Bhuwan

## Sprint5
Sprint # | 5
Start on | 2019-03-15
End on | 2019-03-21
Total Tasks | 10 | Completed | March
Day 1 Left | 10 | 0 | 15
Day 2 Left | 10 | 0 | 16
Day 3 Left | 6 | 4 | 17
Day 4 Left | 6 | 0 | 18
Day 5 Left | 3 | 3 | 19
Day 6 Left | 3 | 0 | 20
Day 7 Left | 0 | 3 | 21
S.N. | Task ID | Type | Assigned To | Description | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for this sprint | COM
2 | REV | Review | Christopher | Review the assigned tasks for this sprint | COM |  | NS | Not Started
3 | ASN2 | Assignment | Anil | Summarize iteration 1 | COM |  | IP | In Progress
4 | ASN2 | Assignment | Anil | Create requirment extension and presentation slides | COM |  | COM | Completed
5 | ASN2 | Assignment | Bhuwan | Prepare demo for the presentation | COM |  |  | Needs Attention
6 | ASN2 | Assignment | Christopher | Create use case, and a report on current features | COM |  | MOV | Moved to next sprint
7 | ASN2 | Assignment | Christopher | Review and complete submissions | COM | Due 03/18 - 9 am
8 | ASN2.2 | Assignment | Anil | Review the iteration document of team 8 and fill up the table | COM |  | Last Updated By
9 | ASN2.2 | Assignment | Bhuwan | Review the iteration document of team 8 and fill up the table | COM
10 | ASN2.2 | Assignment | Christopher | Review the iteration document of team 8 and fill up the table | COM |  | Bhuwan

## Sprint6
Sprint # | 6
Start on | 2019-03-22
End on | 2019-03-28
Total Tasks | 7 | Completed | March
Day 1 Left | 7 | 0 | 22
Day 2 Left | 5 | 2 | 23
Day 3 Left | 5 | 0 | 24
Day 4 Left | 5 | 0 | 25
Day 5 Left | 5 | 0 | 26
Day 6 Left | 3 | 2 | 27
Day 7 Left | 2 | 1 | 28
S.N. | Task ID | Type | Assigned To | Description | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for this sprint | COM
2 | REV | Review | Christopher | Review the assigned tasks for this sprint | COM |  | NS | Not Started
3 | REV | Review | Anil | Review the code implemented so far | MOV | Moved to Sprint 7 | IP | In Progress
4 | REV | Review | Christopher | Review the code implemented so far | MOV | Moved to Sprint 7 | COM | Completed
5 | COD | Coding | Bhuwan | Implement multi-character mode | COM | Moved from Sprint 3 |  | Needs Attention
6 | COD | Coding | Bhuwan | Implement basic character interactions | COM |  | MOV | Moved to next sprint
7 | DEG | Design | Anil | Design game-screen options | COM
8 | DEG | Design | Christopher | Design some event cards | COM |  | Last Updated By
Bhuwan

## Sprint7
Sprint # | 7
Start on | 2019-03-29
End on | 2019-04-04
Total Tasks | 10 | Completed | Mar/Apr
Day 1 Left | 10 | 0 | 29
Day 2 Left | 10 | 0 | 30
Day 3 Left | 10 | 0 | 31
Day 4 Left | 10 | 0 | 1
Day 5 Left | 9 | 1 | 2
Day 6 Left | 8 | 1 | 3
Day 7 Left | 3 | 5 | 4
S.N. | Task ID | Type | Assigned To | Description | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for this sprint | COM
2 | REV | Review | Christopher | Review the assigned tasks for this sprint | COM |  | NS | Not Started
3 | REV | Review | Anil | Review the code implemented so far |  | Removed | IP | In Progress
4 | REV | Review | Christopher | Review the code implemented so far | COM | Moved from Sprint 6 | COM | Completed
5 | IMP | Implementation | Bhuwan | Implement pause menu | COM |  |  | Needs Attention
6 | OPT | Optimization | Bhuwan | Code optimization | COM |  | MOV | Moved to next sprint
7 | COD | Coding | Bhuwan | Implement game end scenario | MOV
8 | IMP | Implementation | Anil | Implement start menu UI | MOV | Moved to Sprint 8 | Last Updated By
9 | DEG | Design | Anil | Design tile effects | COM | Please do this together
10 | DEG | Design | Christopher | Design tile effects | COM |  | Bhuwan

## Sprint8
Sprint # | 8
Start on | 2019-04-05
End on | 2019-04-11
Total Tasks | 13 | Completed | April
Day 1 Left | 13 | 0 | 5
Day 2 Left | 9 | 4 | 6
Day 3 Left | 5 | 4 | 7
Day 4 Left | 5 | 0 | 8
Day 5 Left | 5 | 0 | 9
Day 6 Left | 2 | 3 | 10
Day 7 Left | 0 | 2 | 11
S.N. | Task ID | Type | Assigned To | Discription | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for this sprint | COM
2 | REV | Review | Christopher | Review the assigned tasks for this sprint | COM |  | NS | Not Started
3 | IMP | Implementation | Bhuwan | Implement start menu UI | COM | Moved from Sprint 7 | IP | In Progress
4 | COD | Coding | Christopher | Implement AI | COM | It's implemented, but this'll be a long-running project. | COM | Completed
5 | ASN | Assignment | Anil | Create report and presentation | COM |  |  | Needs Attention
6 | ASN | Assignment | Bhuwan | Review report and presentation | COM |  | MOV | Moved to next sprint
7 | ASN | Assignment | Christopher | Review report and presentation | COM
8 | ASN | Assignment | Anil | Submit assignment | COM |  | Last Updated By
9 | MIS | Miscellaneous | Christopher | Search for sound effects and music | COM | Refer to "Sound effects list" file on the drive
10 | COD | Coding | Bhuwan | Implement tile effects | COM |  | Bhuwan
11 | COD | Coding | Christopher | Implement tile effects | COM
12 | GRA | Graphics | Bhuwan | Design tile effect graphics | COM | Refer to tile effects list
13 | COD | Coding | Bhuwan | Implement message box | COM

## Sprint9
Sprint # | 9
Start on | 2019-04-12
End on | 2019-04-18
Total Tasks | 14 | Completed | April
Day 1 Left | 14 | 3 | 12
Day 2 Left | 14 | 0 | 13
Day 3 Left | 14 | 0 | 14
Day 4 Left | 14 | 0 | 15
Day 5 Left | 14 | 0 | 16
Day 6 Left | 14 | 0 | 17
Day 7 Left | 14 | 0 | 18
S.N. | Task ID | Type | Assigned To | Discription | Status | Comments | Status
1 | REV | Review | Anil | Review the assigned tasks for this sprint | COM
2 | REV | Review | Christopher | Review the assigned tasks for this sprint | COM |  | NS | Not Started
3 | ASN | Assignment | Anil | Iteration 3 review | NS |  | IP | In Progress
4 | ASN | Assignment | Bhuwan | Iteration 3 review | NS |  | COM | Completed
5 | ASN | Assignment | Christopher | Iteration 3 review | NS |  |  | Needs Attention
6 | ASN | Assignment | Anil | Iteration 3 submission | NS | Due 04/15 | MOV | Moved to next sprint
7 | COD | Coding | Anil | Implement sound system | NS
8 | OPT | Optimization | Christopher | Code and AI optimization | NS |  | Last Updated By
9 | COD | Coding | Bhuwan | Implement event cards | NS
10 | IMP | Implementation | Christopher | Implement message displays | NS |  | Bhuwan
11 | IMP | Implementation | Bhuwan | Implement message displays with buttons | NS
12 | IMP | Implementation | Bhuwan | Implement menu credit screen | COM
13 | COD | Coding | Bhuwan | Implement setting in main menu | NS
14 | TES | Testing | Anil | Play the game and report issues | NS